## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	(Fill your team name here)
PROJECT NAME	(Fill your project name here)
PROJECT MENTOR	(Put your Mentor name here)
TEAM MEMBERS	Team Mamber Name 1
	Team Member Name 2
	Team Member Name 3
	Team Member Name 4
	Team Member Name 5

## Team_Status
TEAM NAME	(Fill your team name here)
PROJECT NAME	(Fill your project name here)
PROJECT MENTOR	(Put your Mentor name here)

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 6 (sept 5- sept 11)
Learn Eclipse	Preparation	Elliot	4		Planned	Using IDEs can make our job easier
Role preferences	Coordination	Matt	0.5	0.3	Done		0.2	66.6666666667
SVN Repository setup	Preparation	John	1	1.5	Ongoing		-0.5	33.3333333333
Discuss bug report software	Preparation	Seth	1.5	0	Delayed	This is critical to project success	1.5
Develop questions for requirements elicitation	Documentation	Sean	5		Planned	Make sure scoping questions are included
Get account and configure website	Preparation	Elliot	1.5	1	Done		0.5	50
Research existing technology	Preparation	Matt	2	1.5	Ongoing		0.5	33.3333333333
Project synopsis writeup	Documentation	Elliot	2		Planned
Identify role owners	Preparation	Matt	1	0.6	Done	Multiple roles are OK - think about role & reponsibility distribution	0.4	66.6666666667
Team Meeting	Coordination	John	1	2	Done		-1	50
Status tracker	Documentation	Seth	1		Planned
Week 7 (sept 12 - sept 18)

Week 8 (sept 19 - sept 25)

Week 9

Week 10

Week 11

Week 12

Week 13

Week 14

Week 15

Week 16

Week 17

## Individual_Status
Team Number	17
PROJECT NAME	App8IT
PROJECT MENTOR	Mr Nagarjuna

Actvities	Vatika Harlalka		Shikha Jain		Abhijeet Kumar		Aryaman Gupta		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 4 (aug 28 - sept 4th)
Role preferences	1hour-2hours	1 hour					1 hour - 2hour	1 hour
Git repository setup					10-15 minutes	15 minutes			10-15 minutes	15 minutes
Develop questions for requirements elicitation						30 minutes	1 hour	30 minutes - 1 hour	1 hour
Initial Database Conceptual Design	1 hour- 2hours	4 hours	1 hour - 2 hours	4 hours					1 - 2hours	4 hours
Reseach existing frameworks					1 - 2 hours	3 hours			1-2 hours	3 hours
Project synopsis writeup						1 hour	1 hour	1-2 hours	1 hour
Learn User Profiles and services			1-2 hours	2 hours			1 - 2 hours	2 hours	1-2 hours	2 hours
Team Meeting	1-2 hours	2 hours	1-2 hours	2 hours	1-2 hours	2 hours	1-2 hours	2 hours	1-2 hours	2 hours
Status tracker					30 minutes - 1 hour	30 minutes			30 minutes	30 minutes
Week 5 (sept 5- sept 11)
Learn php						#VALUE!	#VALUE!
Understand Yii						#VALUE!	#VALUE!
Poject Plan Document Writeup						#VALUE!	#VALUE!
Team Meeting						#VALUE!	#VALUE!
Update DB design						#VALUE!	#VALUE!
Make example app						#VALUE!	#VALUE!
Week 6 ( sept 12- sept19 )
Create basic DB						#VALUE!	#VALUE!
Basic Login						#VALUE!	#VALUE!
Registration Admin , Developer, Analyst
Registration User						#VALUE!	#VALUE!
						#VALUE!	#VALUE!
0						#REF!	#REF!
0						#REF!	#REF!
Week 10						#REF!	#REF!
0						#VALUE!	#VALUE!
0						#REF!	#REF!
0						#REF!	#REF!
Week 11						#REF!	#REF!
0						#VALUE!	#VALUE!
0						#REF!	#REF!
0						#REF!	#REF!
Week 12						#REF!	#REF!
0						#VALUE!	#VALUE!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
Week 13						#REF!	#REF!
0						#VALUE!	#VALUE!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
Week 14						#REF!	#REF!
0						#VALUE!	#VALUE!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
Week 15						#REF!	#REF!
0						#VALUE!	#VALUE!
0						#REF!	#REF!
0						#REF!	#REF!
Week 16						#REF!	#REF!
0						#VALUE!	#VALUE!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
Week 17						#REF!	#REF!
0						#VALUE!	#VALUE!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
0						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!
						#REF!	#REF!